PRO/LX - Project Management Add-On for PIM/PE

=============================================

____________

INTRODUCTION

PRO/LX is a utility that works together with PIM/PE and turns "PIM"

from "Personal Information Management" into "Project Information

Management". PRO/LX uses the same file format as PIM/PE and provides a

method to plan tasks and resources. Once you have done the work in

PRO/LX, you can use the resulting PIM file in PIM/PE and the tasks can

be handled in PIM/PE. You thus have all possibilities of PIM/PE to work

with those tasks. For example, you can set filters for specific

resources and create a list of all future dates and tasks in which that

resource is involved.

When developing PRO/LX, the goal was to create something that is as

simple as possible, yet still does useful support for project

management. Most project management (PM) software packages are huge and

complicated and support complex algorithms for critical path

computations, resource leveling etc. When using those packages, there

were always lots of things to be learned, zillions of parameters to be

set and many hours to be spent to find out how to work around the

problem that the program wants to move around certain activities to

places where it should not.

So all this complexity was reduced to a minimum in PRO/LX. I believe

you can do with it at least what you can do with the "big guys" (except

producing colorful printouts) but with much less effort. I don't mean

you can do the same operations, but you can get to the same result.

___________________

QUICK START AND TRY

- Create a directory and put all stuff from PRO.ZIP into it

- Edit PRO.CFG and make sure the file names (File= lines) point

to the files in that directory

- Start the program as "PRO TEST" or "PRO TEST1"

- Play around

_______

CONCEPT

Because PRO/LX does not move around tasks automatically, lots of

parameters are not needed at all (project start date, project end date,

etc.) and only the following parameters are left to be set for each

task:

- a task name

- a planned start date

- an estimated effort to complete the task

- what resources it needs

- on what other tasks it depends on

- optionally: buffers (see further down for an explanation)

while tracking a task, the following parameters are needed in addition

to the above:

- an updated task start date

- an updated estimated task effort

- a "task is completed" state

That's it already. You set up those parameters and PRO/LX detects

potential problems, helping you to move the tasks to a place so that

the whole project plan works, tracks project progress and suggests what

to do when potential problems can be foreseen.

In order to ensure the project plan works out, PRO/LX has adopted some

strategies from "Critical Chain Project Management" (CCPM). See the end

of this text for some references about CCPM.

Of course the simplicity of PRO/LX also leads to some constraints.

These constraints and the basic assumptions that underlie the software

(mostly taken from CCPM) are listed below:

- A project consists of a collection of resources and a number of

tasks that have to be performed according to a certain schedule.

- Project planning is the activity that identifies those resources and

tasks and creates a schedule so that the project can be performed.

- A task is an activity that has a start time and an estimated

effort.

- A resource is either a person involved in a set of tasks or any

"thing" (e.g. a truck or a workstation) that is required for a set

of tasks.

- PRO/LX assumes that 100% of a resource is used for the whole

duration of a task. If a task needs a resource only for a certain

time, the task should be split. Resources are not supposed to be split

among several tasks for the duration of a task (multi-tasking).

- If there are several items of a resource, they are considered

different resources (workstation A, workstation B etc.). They must

be handled separately in PRO/LX.

- PRO/LX is based on days. No fractions of days can be entered. If a

task requires less than one day (but is not just some "event"),

consider if the used granularity is not too fine.

- Only start times of tasks are considered important (and their

estimated effort), not end times as end times tend to provoke

Parkinson's law (work expands to fill - and often exceed - the time

allowed. "Buffer management" is used to make sure the project

completes in time - the project has to complete in time, not the

individual tasks!

- Time buffers are inserted

+ at the end of the project

+ at the end of a task if a different task depends on its

completion and there is "slack", i.e. the task is not on the

critical chain

- PRO/LX considers a buffer to belong to a certain task. A buffer

can be placed at the beginning or the end of a task.

- Progress management can be done by looking at those buffers:

+ if updated task effort estimates extend into the second third

of a buffer, actions should be planned

+ if it extends into the last third, those actions need to be taken

- There is no support for "milestones". There should not be internal

milestones (except the project end) to prevent Parkinson's law. If

several milestones are required towards the "outside" of the

project, the project is best split into smaller projects, each with

a "milestone" at its end.

__________________

PLANNING A PROJECT

In order to set up a project, the following steps need to be done:

1) identify the tasks and resources

2) for each task, enter the following:

- name

- estimated time for task completion in days: 50% chance of

completion - this means WITHOUT any safety time inserted)

- required resources. This is probably the most difficult item

to do because we are used to include lots of safety in our

estimates and provide a value for a 80%-95% estimate.

- which other tasks must be completed before this task can start

3) sort the task so that there is an approximate order (timewise)

4) press F6 (Check) and look at what PRO/LX finds out

5) if PRO/LX has no problems to report, we are done and have a working

project schedule

6) if not, move tasks according to the findings of PRO/LX and go back

to 4)

PRO/LX can report the following problems:

- A task depends on the completion of a different task but is scheduled

so that it should start before the other task is completed. The

solution is to move the depending task to a later date.

- A task requires a resource that is used in a different task at the

same time. This can be solved by moving the task. Note: using a

resource filter displays all tasks in which a resource is involved

and thus makes this activity simpler

- A buffer should be inserted. PRO/LX suggests where buffers should be

inserted and how long they should be.

- A task could start earlier than the current planned starting day.

Move the task back if you want.

- The critical chain is not contiguous. There must be a task that is

on the critical chain that could start earlier or there is a missing

dependency (check dependencies that are based on resources!).

- A task depends on a task A and a task B where task B already depends

on A (transitive dependency). This creates problems. Thus such

dependencies should be removed.

- A buffer is considered too small. Most often, this requires that

you manually move back a whole branch of tasks so that a bigger

buffer can be added.

__________________

TRACKING A PROJECT

While the project is running, periodically (e.g. daily or weekly) do

the following:

1) If not yet done, update the start dates

2) Get new estimates for the needed effort for all tasks in progress

3) Update the estimated effort for all those tasks

(press "u" while task is highlighted)

4) If tasks are completed already, mark them as complete

(press "!" while task is highlighted).

5) Press F8 (Track). PRO/LX will remind you of any missing or obsolete

estimates and recommend actions.

PRO/LX can report the following situations:

- A task that should have started has not yet a start date

- A task that should have started has no or not an updated

effort estimation

- A tasks is endangering a buffer (different kinds of buffers)

- A task could be started earlier than planned because tasks it

depends on are completed earlier than planned

- An updated start date was too optimistic and needs to be moved

again

_______

THE GUI

Most of the display should be self-explanatory. Worthwhile mentioning

are the different types of bars used in the graph though:

Empty rectangle:       task, not yet done

Empty bold rectangle:  task on critical chain, not yet done

Filled rectangle:      task, completed

Grey rectangle:        buffer

Horizontal line:       updated start date and estimated effort

The following key strokes are recognised by PRO/LX. Most of those

functions are also available through the menus (which also list the hot

keys).

F1          display rudimentary online help

SF1         display program version, memory etc.

DOWN        move to next task

UP          move to previous task

PGDN        move down a screenful of tasks

PGUP        move up a screenful of tasks

HOME        move to first task in list

END         move to last task in list

F2          add a new task (starting today, effort of 5 days)

F3          move task up in list

F4          move task down in list

F6          check if schedule contains problems and determine

tasks on critical chain

F8          track project progress

RIGHT       increase start day of task

LEFT        decrease start day of task

Ctrl-LEFT   display earlier dates (scroll horizontally)

Ctrl-RIGHT  display later dates (scroll horizontally)

DEL         delete highlighted task

Ctrl-P      print schedule to file

e           set estimated effort of highlighted task (planning)

u           update effort estimation for highlighted task (tracking)

B           set buffer before highlighted task

b           set buffer after highlighted task

n           change name of highlighted task

r           change resources required for highlighted task

d           change dependencies for highlighted task

y           set the width of a day for the schedule display

h           show "today marker" at a day other than today

Ctrl-s      set project beginning to given date

space       toggle "done" state of task

?           display state and timing information for the highlighted task

ENTER       display task details in PIM format

ALT-Q       terminate program

/ or MENU   display menu

MENU I      set resource filter

_______

PRO.CFG

Lots of options can be set in the configuration file PRO.CFG. The file

consists of several sections.

[Setup] section:

Font=           sets the font to be used: 1=big 2=medium 3=small 4=tiny

name=HFN font. Examples:

Font=3

Font=C:\FONTS\LUHS15.HFN

NameWidth=      sets the width of the task name area in pixels

ResWidth=       sets the width of the resource name area in pixels

DaySize=        sets the width of one day in pixels

DateDeli=       determines which characters are accepted as delimiters

in dates. This setting should match with the same

setting in PIM.CFG and PE.CFG

IsoDate=        if not 0, all dates are displayed in ISO format, i.e.

YYYY-MM-DD. This should also be set the same as in

PIM.CFG and PE.CFG.

BufferSize=     determines the default buffer size. The given value is

in percent of the task or project length. For example if

a value of 50 is given, a buffer is allocated so that it

is about half of the duration of the task (or project)

PrintNameWidth= sets the width of the task name area in characters when

printing

PrintResWidth=  sets the width of the resource name area in characters when

printing

PrintDaySize=   sets the number of days that should be represented by

one character when printing

CriticalPrio=   if set, tasks on the critical chain are saved with the

given priority (e.g. CriticalPrio=a).

DayChar=        specifies the character to be used for "day" in CDF

output. Default is "d" (e.g. "13d" for 13 days).

Delimiter=      specifies the delimiter used for CDF output. Default

is ",".

WithBuffers=    determines if the durations in CDF output include the

buffer durations (WithBuffers=1). Default is: no.

[NoWork] section:

Each line in this section specifies a day which is not a working day.

This can be specified by providing a date or a weekday. Week days are

given as:

0=Mon 1=Tue 2=Wed...6=Sun

Each line must end with an additional "=". Examples:

5=            (Saturday)

6=            (Sunday)

1999-JUL-04   (Holiday)

The remaining sections determine specific projects. If a section is

named, for example, [BuildHouse] and PRO/LX is started with

PRO BuildHouse

Everything is set up according to the data in this section. Each

section must at least contain one line that specifies the PIM file

belonging to the project. Example:

File=C:\PRO\DATA\BUILDHS.PIM

Apart from that entry, you can specify any of the entries that may

appear in the [Setup] section. They will override the values in

[Setup].

If for that project, the dates in [NoWork] do not apply, you may set up

an alternative [NoWork] section and name it, for example, [MyNoWork].

You can then tell PRO/LX that this is the section it should use by

defining

NoWork=MyNoWork

in the project section.

___________________

THE PIM FILE FORMAT

The following format is used to save information about a task:

+( 12-NOV-1999          planned start date

+t Task4                task name

+e 2                    estimated task effort

+s 14-NOV-1999          updated start date

+u 4                    updated task effort

+B 2                    size of buffer before task

+b 8                    size of buffer after task

+c GARZ                 resource needed for task

+< Task1                task that needs to be completed before this one

+)

+. 16-NOV-1999          date on which task was completed

+! Task4 #12-NOV-1999   completion "mark" for given task

_____________

TIPS & TRICKS

*** How to separate projects within PIM/PE

Add a line such as

+C Project1

to the beginning of a project file (but after the time stamp). This

will set category "Project1" for the whole file and you can use a

filter for that category in PIM.

_________________________

CCPM LITERATURE AND LINKS

Larry P. Leach: Critical Chain Project Management

http://www.srv.net/~lleach/

http://advanced-projects.com

Francis S. "Frank" Patrick: Critical Chain Scheduling and Buffer Management

http://www.focusedperformance.com/articles/CCPM.htm

Very good intro to CCPM

Ed D. Walker II: An introduction to Critical Chain Project Management

http://www2.gasou.edu./facstaff/edwalker/ccpm.PDF

Chesapeake Consulting

http://www.chesapeak.com

You can sign up to receive a paper on CCPM which is worth reading

The Product Development Institute - For Speed!    TOC   CCPM -

http://www.pdinstitute.com/

ProChain Solutions Home -- Critical Chain Project Management Solutions -

http://www.prochain.com

Fran Stone Enterprises - TOC  Jonah's Jonah -

http://members.aol.com/FStoneEnt/index.html

Eliyahu Goldratt  The Goal    Crazy About Constraints! -

http://www.rogo.com/cac/index.html

Dr Holt  TOC Power Point Presentations -

http://www.vancouver.wsu.edu/fac/holt/em526/ppt.htm

Constraints Management SIG--Theory of Constraints -

http://www.apics.org/sigs/CM/TOC.htm

Constraint Accounting Measurements       John Caspari -

http://members.aol.com/caspari/

CIRAS - Theory of Constraints -

http://www.ciras.iastate.edu/toc/index.html

Bill Dettmer from Goal Systems International -

http://www.goalsys.com/

AMC Homepage       TOC consulting -

http://www.wvamc.com/

---

Andreas Garzotto, 24-Nov-99